## 10x10 sample
|  | a | b | c | d | e | f | g | h | i | j | zzz | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z
key |  | A | B | C | D | E | F | G | H | I | J | [13 empty] | start | soln | soln2
a | A | [10 empty] | A | [12 empty] | a | b3 | b3 | bar: a A; c C; e E; j J
b | B | [10 empty] | B | [12 empty] | b | f | d3 | bar: a A to c C; h H to i I
c | C | [10 empty] | C | [12 empty] | c | a | a | bar: c C
d | D | [10 empty] | D | [12 empty] | d | d | h | bar: d D to e E; g G; j J
e | E | [10 empty] | E | [12 empty] | e | b2 | b2 | bar: a A; e E; j J
f | F | [10 empty] | F | [12 empty] | f | q | z | bar: a A to d D; f F to g G
g | G | [10 empty] | G | [12 empty] | g | e | h | bar: d D; g G; j J
h | H | [10 empty] | H | [12 empty] | h | g | d2 | bar: b B; e E; h H; j J
i | I | [10 empty] | I | [12 empty] | i | e | d1 | bar: a A to c C; i I
j | J | [10 empty] | J | [12 empty] | j | b1 | b1 | bar: c C; e E; j J
zzz |  | A | B | C | D | E | F | G | H | I | J | [13 empty] | zzz | zzz | zzz
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Sort
Box
Dash

## 10x10 sample (soln)
|  | a | b1 | b2 | b3 | d | e | e | f | g | q | zzz | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z | Z
soln1 |  | C | J | E | A | D | G | I | B | H | F | [13 empty] | start | soln1 | soln2
a | C | [10 empty] | C | [12 empty] | c | a | a | bar: C
b1 | J | [10 empty] | J | [12 empty] | j | b1 | b1 | bar: C to E
b2 | E | [10 empty] | E | [12 empty] | e | b2 | b2 | bar: J to A
b3 | A | [10 empty] | A | [12 empty] | a | b3 | b3 | bar: C to A
d | D | [10 empty] | D | [12 empty] | d | d | h | bar: J to E; d D to e G
e | G | [10 empty] | G | [12 empty] | g | e | h | bar: J; d D to e G
e | I | [10 empty] | I | [12 empty] | i | e | d1 | bar: C; A; e I to f B
f | B | [10 empty] | B | [12 empty] | b | f | d3 | bar: C; A; e I to g H
g | H | [10 empty] | H | [12 empty] | h | g | d2 | bar: J to E; f B to g H
q | F | [10 empty] | F | [12 empty] | f | q | z | bar: C; A to e G; f B; q F
zzz |  | C | J | E | A | D | G | I | B | H | F | [13 empty] | zzz | zzz | zzz
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z
Z | [24 empty] | Z | Z | Z

## Plant DSM
|  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
start |  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U |  | ACTIVITY NAMES | 4B | B+ | start
A | A | [21 empty] | A | Specification | a10 | A | A | bar: A A
B | B | [21 empty] | B | Schedules | a11 | B | B | bar: A A to C C; E E
C | C | [21 empty] | C | Purchasing Plan | a12 | d | C | bar: A A to E E
D | D | [21 empty] | D | Quality Plan | a13 | a1 | D | bar: A A; D D
E | E | [21 empty] | E | Manufacturing Plan | a14 | c | E | bar: A A to E E
F | F | [21 empty] | F | Process Engineering | a15 | g | F | bar: A A; D D; F F to G G; M M; O O
G | G | [21 empty] | G | Dimensioning | a16 | f | G | bar: A A; D D; F F to H H; J J to L L
H | H | [21 empty] | H | Pressure Parts | a19 | H | H | bar: A A; E E; G G to H H
I | I | [21 empty] | I | Layout Steel | a20 | j | I | bar: A A; H H to L L
J | J | [21 empty] | J | Layout Ductwork | a21 | i | J | bar: A A; F F; I I to L L
K | K | [21 empty] | K | Layout Piping | a22 | k | K | bar: A A; F F; H H to L L
L | L | [21 empty] | L | Main Layout | a23 | e | L | bar: A A; L L
M | M | [21 empty] | M | Instrumentation | a17 | g | M | bar: A A; D D; F F to G G; M M
N | N | [21 empty] | N | Electronics | a26 | x | N | bar: A A; M M to N N; Q Q to U U
O | O | [21 empty] | O | Automation Layout | a18 | g | O | bar: A A; D D; F F; M M; O O
P | P | [21 empty] | P | Automation Details | a25 | y | P | bar: A A; N N to P P
Q | Q | [21 empty] | Q | Basic Engineering | a24 | Q | Q | bar: A A; D D to F F; H H; N N; Q Q
R | R | [21 empty] | R | Piping Details | a27 | R | R | bar: A A; D D; K K; N N; Q Q to R R; U U
S | S | [21 empty] | S | Ductwork Details | a28 | S | S | bar: A A; J J; N N; Q Q; S S; U U
T | T | [21 empty] | T | Steel Details | a29 | T | T | bar: A A; I I; N N; T T
U | U | [21 empty] | U | Main Auxiliaries | a30 | p | U | bar: A A; L L; N N; U U
|  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
Commands
a sort order
k save order
g solid box
j dash box
h undo box

## Plant-boxed
|  | A | a1 | B | c | d | e | f | g | g | g | H | i | j | k | p | Q | R | S | T | x | y
boxes |  | A | D | B | E | C | L | G | F | M | O | H | J | I | K | U | Q | R | S | T | N | P |  | ACTIVITY NAMES | solution | practice | start
A | A | [21 empty] | A | Specification | a10 | a | A | bar: A
a1 | D | [21 empty] | D | Quality Plan | a13 | a3 | D | bar: A to D
B | B | [21 empty] | B | Schedules | a11 | b1 | B | bar: A; B B to d C
c | E | [21 empty] | E | Manufacturing Plan | a14 | b3 | E | bar: A to d C
d | C | [21 empty] | C | Purchasing Plan | a12 | d | C | bar: A to d C
e | L | [21 empty] | L | Main Layout | a23 | a2 | L | bar: A; e L
f | G | [21 empty] | G | Dimensioning | a16 | a7 | G | bar: A to D; e L to g F; H H to i J; k K
g | F | [21 empty] | F | Process Engineering | a15 | d | F | bar: A to D; f G to g O
g | M | [21 empty] | M | Instrumentation | a17 | a8 | M | bar: A to D; f G to g M
g | O | [21 empty] | O | Automation Layout | a18 | a9 | O | bar: A to D; g F to g O
H | H | [21 empty] | H | Pressure Parts | a19 | b1 | H | bar: A; c E; f G; H H
i | J | [21 empty] | J | Layout Ductwork | a21 | b3 | J | bar: A; e L; g F; i J to k K
j | I | [21 empty] | I | Layout Steel | a20 | b2 | I | bar: A; e L; H H to k K
k | K | [21 empty] | K | Layout Piping | a22 | b4 | K | bar: A; e L; g F; H H to k K
p | U | [21 empty] | U | Main Auxiliaries | a30 | d | U | bar: A; e L; p U; x N
Q | Q | [21 empty] | Q | Basic Engineering | a24 | b6 | Q | bar: A to D; c E; g F; H H; Q Q; x N
R | R | [21 empty] | R | Piping Details | a27 | b9 | R | bar: A to D; k K to R R; x N
S | S | [21 empty] | S | Ductwork Details | a28 | d | S | bar: A; i J; p U to Q Q; S S; x N
T | T | [21 empty] | T | Steel Details | a29 | d | T | bar: A; j I; T T to x N
x | N | [21 empty] | N | Electronics | a26 | b8 | N | bar: A; g M; p U to x N
y | P | [21 empty] | P | Automation Details | a25 | z | P | bar: A; g O; x N to y P
|  | A | D | B | E | C | L | G | F | M | O | H | J | I | K | U | Q | R | S | T | N | P
Commands
a sort order
k save order
g solid box
j dash box
h undo box

## Plant-boxed+
|  | a10 | a11 | a12 | a13 | a14 | a15 | a16 | a17 | a18 | a19 | a20 | a21 | a22 | a23 | a24 | a25 | a26 | a27 | a28 | a29 | a30
|  | A | B | C | D | E | F | G | M | O | H | I | J | K | L | Q | P | N | R | S | T | U |  | ACTIVITY NAMES | solution | practice | start
a10 | A | [21 empty] | A | Specification | a10 | a | A | bar: a10 A
a11 | B | [21 empty] | B | Schedules | a11 | b1 | B | bar: a10 A to a12 C; a14 E
a12 | C | [21 empty] | C | Purchasing Plan | a12 | d | C | bar: a10 A to a14 E
a13 | D | [21 empty] | D | Quality Plan | a13 | a3 | D | bar: a10 A; a13 D
a14 | E | [21 empty] | E | Manufacturing Plan | a14 | b3 | E | bar: a10 A to a14 E
a15 | F | [21 empty] | F | Process Engineering | a15 | d | F | bar: a10 A; a13 D; a15 F to a18 O
a16 | G | [21 empty] | G | Dimensioning | a16 | a7 | G | bar: a10 A; a13 D; a15 F to a16 G; a19 H; a21 J to a23 L
a17 | M | [21 empty] | M | Instrumentation | a17 | a8 | M | bar: a10 A; a13 D; a15 F to a17 M
a18 | O | [21 empty] | O | Automation Layout | a18 | a9 | O | bar: a10 A; a13 D; a15 F; a17 M to a18 O
a19 | H | [21 empty] | H | Pressure Parts | a19 | b1 | H | bar: a10 A; a14 E; a16 G; a19 H
a20 | I | [21 empty] | I | Layout Steel | a20 | b2 | I | bar: a10 A; a19 H to a23 L
a21 | J | [21 empty] | J | Layout Ductwork | a21 | b3 | J | bar: a10 A; a15 F; a20 I to a23 L
a22 | K | [21 empty] | K | Layout Piping | a22 | b4 | K | bar: a10 A; a15 F; a19 H to a23 L
a23 | L | [21 empty] | L | Main Layout | a23 | a2 | L | bar: a10 A; a23 L
a24 | Q | [21 empty] | Q | Basic Engineering | a24 | b6 | Q | bar: a10 A; a13 D to a15 F; a19 H; a24 Q; a26 N
a25 | P | [21 empty] | P | Automation Details | a25 | z | P | bar: a10 A; a18 O; a25 P to a26 N
a26 | N | [21 empty] | N | Electronics | a26 | b8 | N | bar: a10 A; a17 M; a24 Q; a26 N to a30 U
a27 | R | [21 empty] | R | Piping Details | a27 | b9 | R | bar: a10 A; a13 D; a22 K; a24 Q; a26 N to a27 R; a30 U
a28 | S | [21 empty] | S | Ductwork Details | a28 | d | S | bar: a10 A; a21 J; a24 Q; a26 N; a28 S; a30 U
a29 | T | [21 empty] | T | Steel Details | a29 | d | T | bar: a10 A; a20 I; a26 N; a29 T
a30 | U | [21 empty] | U | Main Auxiliaries | a30 | d | U | bar: a10 A; a23 L; a26 N; a30 U
|  | A | B | C | D | E | F | G | M | O | H | I | J | K | L | Q | P | N | R | S | T | U
Planning
Process Engineering
Layout
Details
Commands
a sort order
k save order
g solid box
j dash box
h undo box

## instructions
The sorting macro is in the macro sheet. Note that the macro does not automatically
repartition the matrix. It only automates the manual swapping of rows and columns. There
are simple algorithms for sequencing (partitioning) available but I have not found much
use for these. Unfortunately I do not have robust software yet available that does all I
would like it to do.
You will need some instructions from me if you are to try to work on this: first of all, you
need to set up your matrix with an extra column, say the first column. Then leave a blank
row somewhere, say the first row. This column is for you to use to add the sorting keys.
You simply place text in each cell which tells the macro how to order the rows
alphabetically. So if you give the first 5 rows of the matrix the keys a, b3, b1, c, b0, they
will be reordered to a, b0, b1, b3, c. The macro first copies this key column into the key
row (transposed). Then it sorts the matrix rows according to the keys and then sorts the
columns the same way. You can use this to manually order a matrix without the tedium of
cutting, dragging, and pasting.
This macro works on a 20x20 matrix. You can change it to any size you like by changing
the number 23 to another number in three places. You will see that the key column is C1
and the key row is R1. I hope that you can figure the details as necessary. Good luck.

## Macros
CopyTransposeSort (a) | SaveOrder (k) | BoxOutline (g) | DashedBorder (j) | UndoBorders (h)
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME?
#NAME?
#NAME?
#NAME?